## Dashboard
TexaWave ERP - Finance API Test Status Dashboard
Suite: Postman Finance Operations (Payments Received, Expenses & Security Checks) ¦ As of 24-Oct-2026
Total Tasks |  | Completed |  | % Tests Done |  | Blocked |  | Need to Discuss / Fail |  | Pending
44 |  | 30 |  | 68.18% |  | 0 |  | 0 |  | 28
Status Breakdown |  |  |  |  | API Suite Breakdown (Live Rollup)
Status | Tasks | % of Tasks | Completed Qty |  | API Suite / Module | Total Checks | Completed | Pending | Blocked | % Done | Suite Status
Completed | 30 | 68.18% | 30 |  | Payments Received API | 19 | 19 | 0 | 0 | 100% | Completed
In Progress | 0 | 0% | 0 |  | Expenses API | 10 | 10 | 0 | 0 | 100% | Completed
In Review | 0 | 0% | 0 |  | Pending API Checks | 15 | 1 | 28 | 0 | 6.667% | In Progress
Pending | 28 | 63.64% | 0 |  | Total All Suites | 44 | 30 | 28 | 0 | 68.18% | In Progress
Blocked | 0 | 0% | 0
Need to Discuss | 0 | 0% | 0
Not Started | 0 | 0% | 0
Total | 58 | 131.8% | 30

## Payments Received API
TexaWave ERP - Payments Received API Tracker (Postman Manual Test Cases)
Do not edit the navy columns (API test spec). Update Status ('Completed' button), % Done, Actual Result / Notes, and Last Updated. Dashboard updates automatically.
Test ID | Test Method | URL | JSON Code for Test | Expected Result | Explanation / Steps to Do | Prerequisites / Variables | Status | % Done | Actual Result / Notes | Last Updated
PR-001 | POST | {{baseUrl}}/auth/login | { "organizationSlug": "{{organizationSlug}}", "email": "{{email}}", "password": "{{password}}" } | Expected per project guide: 201 Created; response contains data.accessToken. | Set Body → raw → JSON, enter your real local credentials, click Send, save data.accessToken as accessToken. Check current auth controller if status differs. | baseUrl, organizationSlug, email, password | Completed | 100% | 201 OK (121 MS)
PR-002 | GET | {{baseUrl}}/finance-settings/master-list-items?category=payment_mode&limit=10 | (No body) | 200 OK with payment mode items; save a real item id as paymentModeId. | Add Bearer token. Click Send. Pick an active payment mode from the response; do not guess its ID. | accessToken; finance settings read permission | Completed | 100% | 200 OK (46MS)
PR-003 | GET | {{baseUrl}}/finance/bank-accounts | { "invoiceReference": "TEST-INV-TOO+D21 | Expected 200 OK if route and permission are enabled; save an eligible bankAccountId. | Send with Bearer token. If no account exists, mark BLOCKED and ask for a test account to be seeded. | accessToken; check current controller/permission | Completed | 100% | 200 OK (26 MS)
PR-004 | GET | {{baseUrl}}/crm/accounts?type=CUSTOMER | (No body) | Expected 200 OK if this route/query matches the current CRM API; save a real customerId. | Send with Bearer token. If route differs, inspect current CRM controller and update URL; do not guess IDs. | accessToken; CRM read permission | Completed | 100% | 200 OK (23 MS)
PR-005 | POST | {{baseUrl}}/finance/payments-received | { "paymentDate": "2026-10-23", "amount": 8000.00, "paymentModeId": {{paymentModeId}}, "customerName": "Globex Corporation", "referenceNumber": "TEST-NEFT-001", "notes": "Postman test - customer advance", "status": "DRAFT", "allocations": [ {"invoiceReference": "TEST-INV-0044", "allocatedAmount": 3000.00, "notes": "Test partial allocation"}, {"invoiceReference": "TEST-INV-0045", "allocatedAmount": 2000.00, "notes": "Test second allocation"} ] } | Expected 201 Created per guide. amount=8000, allocatedAmount=5000, unallocatedAmount=3000, status=DRAFT. Save data.id as paymentReceivedId and first allocation id as allocationId. | Use test data. Important: current DTO may require customerId instead of customerName and may require bankAccountId. Check current DTO; adapt body accordingly before sending. | accessToken, paymentModeId; customerId/bankAccountId if required | Completed | 100% | 200 OK (26 MS), paymentmodeid 7, payment recive id : (7) 14
PR-006 | GET | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}} | (No body) | 200 OK; id matches and details/allocations persist. | Run after create succeeds. Compare amount, status, allocation rows and totals. | paymentReceivedId; read permission | Completed | 100% | 200 OK (129 MS)
PR-007 | GET | {{baseUrl}}/finance/payments-received?page=1&limit=10&status=DRAFT | (No body) | 200 OK with paginated list and metadata; created draft should appear. | Find the created receipt in the result and check pagination metadata. | read permission | Completed | 100% | 200 OK (61 MS)
PR-008 | PATCH | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}} | { "referenceNumber": "TEST-NEFT-UPDATED-001", "notes": "Updated reference during Postman test" } | Expected 200 OK; reference and notes updated, totals unchanged. | Use a DRAFT test receipt. Send JSON, then GET the receipt again to verify persistence. | paymentReceivedId; write permission | Completed | 100% | 200 OK (11 MS)
PR-009 | POST | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}}/allocations | { "invoiceReference": "TEST-INV-0046", "allocatedAmount": 500.00, "notes": "Additional allocation test" } | Expected 201 per guide. If initial allocation was 5000, allocatedAmount=5500 and unallocatedAmount=2500. | Ensure at least 500 remains unallocated. Send; record actual response shape because audit reported frontend/backend return-type mismatch. | paymentReceivedId; write permission; enough unallocated amount | Completed | 100% | 201 OK (41 MS)
PR-010 | DELETE | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}}/allocations/{{allocationId}} | (No body) | Expected 204 No Content; allocation removed and unallocated balance increases by its amount. | Use allocationId from create response. Then GET receipt and check totals. Test record only. | paymentReceivedId, allocationId; write permission | Completed | 100% | 204 NO CONTENT (18 MS)
PR-011 | POST | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}}/confirm | {} | Expected per guide: 201 Created, status=CONFIRMED, journalEntryId exists; journal debits equal credits. | Only use a dedicated test receipt in a safe dev DB. Send {}. Inspect journal details if exposed. Never do this on production data. | paymentReceivedId; write permission; safe test DB | Completed | 100% | 201 Created (15 MS)
PR-012 | POST | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}}/confirm | {} | Expected 422 or documented conflict; second confirmation must not create a duplicate journal. | Run only after test receipt was confirmed. Send again and verify rejection/no duplicate journal. | Already-confirmed test receipt | Completed | 100% | EXPECTED 422 ALREDY CREATED (11 MS)
PR-013 | POST | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}}/void | {} | Expected per guide: 201 Created, status=VOID, reversal journal exists and balances are reversed. | Only run on a confirmed test receipt in safe dev DB. Inspect original and reversal journals. | Confirmed test receipt; write permission | Completed | 100% | 201 created (49 MS)
PR-014 | DELETE | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}} | (No body) | Expected 204 No Content; soft-delete allowed for VOID receipt. | Only run after void test on test data. Verify list/detail behavior matches API contract. | VOID test receipt; write permission | Completed | 100% | 404 no content
PR-015 | POST | {{baseUrl}}/finance/payments-received | { "paymentDate": "2099-01-01", "amount": 1000, "paymentModeId": {{paymentModeId}}, "customerName": "Future Date Test", "referenceNumber": "TEST-FUTURE-DATE", "status": "DRAFT", "allocations": [] } | Expected 422 FUTURE_PAYMENT_DATE or equivalent; no receipt created. | Separate negative test. Adapt customer fields to current DTO, send, then check list to ensure no record was created. | paymentModeId; write permission | Completed | 100% | 422 EXPECTED BUT IT SAYS ,Unprocessable Entity (WebDAV) (RFC 4918)
PR-016 | POST | {{baseUrl}}/finance/payments-received | { "paymentDate": "2026-10-23", "amount": 1000, "paymentModeId": {{paymentModeId}}, "customerName": "Over Allocation Test", "referenceNumber": "TEST-OVERALLOC-001", "status": "DRAFT", "allocations": [ {"invoiceReference": "TEST-INV-OVER", "allocatedAmount": 1200, "notes": "Intentional invalid over-allocation"} ] } | Expected 422 EXCEEDS_PAYMENT_AMOUNT or equivalent; no receipt created. | Separate negative test. Verify API rejects allocations totalling more than payment amount. | paymentModeId; write permission | Completed | 100% | 422 EXPECTED BUT IT SAYS ,Unprocessable Entity (WebDAV) (RFC 4918)
PR-017 | POST | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}}/allocations | { "invoiceReference": "TEST-INV-TOO-LARGE", "allocatedAmount": 999999, "notes": "Intentional invalid allocation" } | Expected 422 EXCEEDS_UNALLOCATED_BALANCE or equivalent; totals remain unchanged. | Use a DRAFT test receipt with less than 999999 unallocated. Send, then GET and compare totals. | paymentReceivedId; write permission | Completed | 100% | EXPECTED 422 (47 MS)
PR-018 | GET | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}} | (No Authorization header) | Expected 401 Unauthorized. | Override Authorization to No Auth for this one request, send, then restore inherited auth. | No token for this test | Completed | 100% | 401 unauthorized
PR-019 | PATCH | {{baseUrl}}/finance/payments-received/{{paymentReceivedId}} | { "referenceNumber": "SHOULD-NOT-UPDATE", "notes": "Attempt to edit void receipt" } | Expected documented rejection (audit suggests 422) for immutable VOID receipt. | Run only with a VOID test receipt. Send and verify record remains unchanged. | VOID test receipt; write permission | Completed | 100% | EXPECTED

## Expenses API
TexaWave ERP - Expenses API Tracker (Lifecycle: DRAFT → SUBMIT → APPROVE → PAY → CANCEL)
Do not edit the navy columns (API test spec). Update Status ('Completed' button), % Done, Actual Result / Notes, and Last Updated. Dashboard updates automatically.
Test ID | Test Method | URL | JSON Code for Test | Expected Result | Explanation / Steps to Do | Prerequisites / Variables | Status | % Done | Actual Result / Notes | Last Updated
EXP-001 | POST | {{baseUrl}}/finance/expenses | { "expenseTypeId": {{expenseTypeId}}, "expenseDate": "2026-10-23", "amount": 3000.00, "taxAmount": 540.00, "paymentModeId": {{paymentModeId}}, "vendorName": "Apex Office Hub", "referenceNumber": "TEST-EXP-001", "notes": "Postman test - workstation equipment", "status": "DRAFT" } | Expected 201; status=DRAFT; netAmount may equal 3540 if net is amount plus tax. Save data.id as expenseId. | Discover expenseTypeId and paymentModeId first. Send as raw JSON; check current DTO for required fields. | expenseTypeId, paymentModeId; write permission | Completed | 100% | expected 201
EXP-002 | GET | {{baseUrl}}/finance/expenses/{{expenseId}} | (No body) | 200 OK; expense detail returned with status DRAFT. | Run after create; verify id, amount, status and fields. | expenseId; read permission | Completed | 100% | 200 OK
EXP-003 | GET | {{baseUrl}}/finance/expenses?status=DRAFT&page=1&limit=10 | (No body) | 200 OK; list includes the draft and pagination metadata. | Find expense by ID in result. | read permission | Completed | 100% | 200 OK
EXP-004 | PATCH | {{baseUrl}}/finance/expenses/{{expenseId}} | { "amount": 3200.00, "taxAmount": 576.00, "notes": "Updated test amount" } | Expected 200; netAmount may equal 3776 if the current rule is amount + tax. | Update only a DRAFT test expense. GET it again to verify. | expenseId; write permission | Completed | 100% | 200 OK
EXP-005 | POST | {{baseUrl}}/finance/expenses/{{expenseId}}/submit | {} | Expected 201 per guide; status=PENDING_APPROVAL. | Run after draft is created; verify response/GET. | expenseId; write permission | Completed | 100% | 201 created
EXP-006 | POST | {{baseUrl}}/finance/expenses/{{expenseId}}/approve | {} | Expected 201 per guide; status=APPROVED. | Run only after submission; use an authorized test role. | expenseId; approval permission | Completed | 100% | 201 created
EXP-007 | POST | {{baseUrl}}/finance/expenses/{{expenseId}}/pay | { "paymentDate": "2026-10-23", "referenceNumber": "TEST-NEFT-EXP-001" } | Expected 201 per guide; status=PAID, journalEntryId exists and journal is balanced. | Only on an APPROVED test expense in safe dev DB. Inspect journal details. | expenseId; APPROVED test expense | Completed | 100% | Exxpected 201
EXP-008 | POST | {{baseUrl}}/finance/expenses/{{expenseId}}/cancel | {} | Expected 201 per guide; status=CANCELLED and reversal journal exists. | Only after successful test payment. Verify reversal journal balances. | PAID test expense | Completed | 100% | 201 created
EXP-009 | DELETE | {{baseUrl}}/finance/expenses/{{expenseId}} | (No body) | Expected 204; soft-delete permitted after cancellation. | Only on cancelled test expense. Verify list/detail behavior. | CANCELLED test expense | Completed | 100% | 204 No Content
EXP-010 | POST | {{baseUrl}}/finance/expenses | { "expenseTypeId": {{expenseTypeId}}, "expenseDate": "2099-01-01", "amount": 1000, "taxAmount": 0, "paymentModeId": {{paymentModeId}}, "vendorName": "Future Date Negative Test", "referenceNumber": "TEST-EXP-FUTURE", "notes": "Intentional invalid future date", "status": "DRAFT" } | Expected 422 FUTURE_EXPENSE_DATE or equivalent; no record created. | Separate negative test; verify no record was created. Adapt body to current DTO. | expenseTypeId, paymentModeId; write permission | Completed | 100% | 422 Expected

## Pending API Checks
TexaWave ERP - Pending API & Security Verification Tracker (Audit & Risk Backlog)
Do not edit the navy columns (Verification spec). Update Status ('Completed' button), % Done, Evidence / Notes, and Last Updated. Dashboard updates automatically.
Check ID | Area | API / Check | Why Pending / Risk | How to Verify | Expected Result / Acceptance Criteria | Priority | Status | % Done | Evidence / Notes | Last Updated
CHK-001 | Payments Received | Create → GET → list | Prepared guide does not prove live requests were executed. | Run create, detail and list rows; save sanitized responses. | Created receipt persists and appears in detail/list. | P1 | PASS | 100%
CHK-002 | Payments Received | Confirm + GL posting | Live database posting not proven by unit tests alone. | Confirm a test receipt and inspect journal detail. | CONFIRMED; one journal only; total debits = total credits. | P1 | Pending | 0%
CHK-003 | Payments Received | Void + reversal | Live reversal still needs manual verification. | Void a confirmed test receipt and inspect original/reversal journals. | VOID; original journal reversed; reversal balances. | P1 | Pending | 0%
CHK-004 | Payments Received | Allocation arithmetic | Need to verify persisted totals after add/remove. | GET receipt after every allocation change. | allocatedAmount equals allocation sum; unallocatedAmount equals amount minus allocated. | P1 | Pending | 0%
CHK-005 | Payments Received | Overdue/due-month filters | Audit found client-side filtering of only current page and no authoritative SalesInvoice model. | Inspect DTO/repository; test with more than 15 records if possible. | No advance credit labelled overdue; accurate server-side counts or unsupported filter disabled. | P0 | Pending | 0%
CHK-006 | Payments Received | Invoice source and status synchronization | Invoice reference is free text; project guide says no dedicated SalesInvoice model. | Inspect schema and Sales integration; document dependency. | Do not claim live invoice balance, due date or payment-status sync without authoritative source. | P1 | Pending | 0%
CHK-007 | Payments Received UI | Edit draft action | Audit reports PATCH exists but UI edit action is missing. | After implementation, edit DRAFT in UI then GET via API. | Draft can be edited; confirmed/reconciled/void remain restricted. | P2 | Pending | 0%
CHK-008 | Payments Received API | Allocation response typing | Audit reports frontend type differs from backend response. | Compare controller/service response with api.ts and run allocation request. | Frontend type matches actual backend payload. | P2 | Pending | 0%
CHK-009 | Security | Unauthenticated request | Needs live security check. | Send protected GET without Authorization. | 401; no protected data returned. | P1 | Pending | 0%
CHK-010 | Security | Write permission denial | Requires a read-only test account. | POST using token without write permission. | 403; no record created. | P1 | Pending | 0%
CHK-011 | Security | Tenant isolation | Requires two test organizations. | Try Org A's record ID using Org B token. | No cross-tenant data leakage; project contract expects 404. | P1 | Pending | 0%
CHK-012 | Expenses | Draft → submit → approve → pay → cancel | Prepared manual tests need live execution. | Run lifecycle on a test-only expense. | Correct states and balanced posting/reversal entries. | P1 | Pending | 0%
CHK-013 | UI/API E2E | Browser to API workflow | Audit says no Playwright UI E2E spec exists for this feature. | Manually create, allocate, filter, print and inspect persistence; automate when test infra exists. | UI payloads match API; visible state matches persisted state. | P1 | Pending | 0%
CHK-014 | Test infrastructure | Disposable E2E DB and Redis | Project notes say harness safely aborted because test DB/Redis unavailable. | Follow repository e2e-guard instructions to configure isolated services. | E2E runs only against disposable test DB and dedicated Redis, never texawave_erp. | P1 | Pending | 0%
CHK-015 | Request contract | Customer and bank prerequisites | Docs vary between customerName/customerId and optional/required bankAccountId. | Compare current DTO and controller; run discovery requests. | Requests use actual required fields and real IDs. | P1 | Pending | 0%

## How to Update
How to Update the Finance API Test Tracker
1. Open 'Payments Received API', 'Expenses API', or 'Pending API Checks' and pick the test case row you are executing.
2. Click the Status pill button in Column H and select 'Completed' once the Postman request passes all Expected Result checks.
3. Use 'Blocked' or 'Need to Discuss' (or 'FAIL') immediately if a route, DTO contract, or database prerequisite fails — do not wait.
4. Always record sanitized response evidence or error details in Column J ('Actual Result / Notes') and put today's date in Column K ('Last Updated' — Ctrl + ;).
5. Do not edit the navy columns (Columns A–G test specification data). The Dashboard and % Done counters update automatically.
Example: Status = Completed ¦ % Done = 100% ¦ Actual Result = '201 Created; paymentReceivedId saved; journalEntryId balanced'
Status Button | When to use it
Completed | Request executed in Postman and actual HTTP status, payload, and DB persistence match Expected Result.
In Progress | Currently configuring prerequisites, tokens, or actively testing the endpoint.
In Review | Endpoint tested; response or DTO mismatch raised for PR/backend review.
Pending | Default initial state — manual verification has not been executed yet.
Blocked | Cannot execute due to missing seed data, unavailable test DB/Redis, or missing route/permission.
Need to Discuss | Contract caveat or unexpected 422/500 behavior that requires team discussion.
Not Started | Test suite scheduled for a later sprint phase.
Postman Runbook Topic | Operational Instructions (from Original Workbook)
Purpose | Manual API test cases for Finance Operations while UI implementation continues. All test statuses start as PENDING; mark PASS only after executing the request.
Safety | Use only local development/test data. Never run confirm, void, cancel, or delete requests against production or real financial records.
Setup | Start the API using the repository's normal command. Use the actual API port from the terminal; do not assume the example port is correct.
Postman import | Import postman/finance-api.postman_collection.json and postman/finance-local.postman_environment.json from the repository if present.
Environment | Set baseUrl, organizationSlug, email, password using real development values. Never share passwords or access tokens.
Login | POST {{baseUrl}}/auth/login. Project guide expects data.accessToken. Save it as accessToken and use Authorization: Bearer {{accessToken}} for protected routes.
Discover IDs | Run payment-mode, bank-account, and customer discovery requests first. Use IDs from real API responses; never guess IDs.
Run a request | Choose method and URL, use Body → raw → JSON for JSON bodies, click Send, then compare status and response with Expected Result.
Record outcome | Update Status to PASS, FAIL, BLOCKED, or PENDING and add sanitized evidence in Actual Result / Notes.
Contract caveat | Project docs contain examples using customerName and others using customerId. Verify the current DTO/controller before sending create requests; adapt the body to the actual contract.
Invoice caveat | The available project notes say there is no dedicated SalesInvoice Prisma model. Invoice references here are test strings and do not prove invoice balance/status synchronization.
E2E caveat | Project notes say the E2E harness was blocked because a disposable test database and dedicated Redis were unavailable. These manual checks remain pending until executed safely.

## Project Info
Project Info — TexaWave ERP Finance API Verification
Metric | Value | Notes
Workbook Name | TexaWave ERP — Finance Postman API Test Tracker | Redesigned to match TexaWave_ERP_Sprint_Plan_Revised architecture
Target Environment | Local Development API + Disposable Test DB | Never run confirm, void, cancel, or delete against production records
Payments Received Tests | 19 Manual API Test Cases (PR-001 to PR-019) | Covers Auth, Discovery, Create, Allocate, Confirm, Void, Delete & Negative 422s
Expenses API Tests | 10 Manual API Test Cases (EXP-001 to EXP-010) | Covers Draft, GET, PATCH, Submit, Approve, Pay, Cancel, Delete & Future Date 422
Pending API & Security Checks | 15 Audit & Risk Checks (CHK-001 to CHK-015) | Covers GL posting, reversal, RBAC 401/403, tenant isolation 404, and E2E guard
Total Verification Items | 44 | Automatically summed across all 3 tracker sheets
Contract Caveat | customerName vs customerId & bankAccountId | Verify current DTO/controller before sending create requests
Invoice Caveat | No dedicated SalesInvoice Prisma model | Invoice references are free-text strings; do not claim live invoice sync