## Dashboard & Overall Status
TexaWave ERP — Finance Module Executive Engineering & QA Dashboard
Source of Truth Implementation Audit ¦ Active Branch: feature/finance ¦ Release Scope: 26 October 2026
Documented Endpoints | Prisma Models | Unit Tests Passing | Total Postman Tests | Completed / Pass | Pending Live Verif.
74 | 11 | 312/312 | 98 | 31 | 67
10 Finance Modules | 186 Scalar DB Fields | 100% Green (23 Files) | 44 Preserved + 54 New | Live Postman Verified | Awaiting Local Dev Run
Finance Module Implementation & Ticket Status Matrix
Finance Module | Ticket Ref | Backend Status | Frontend Status | Test Results & Scope | Architecture Notes
Operating Expenses | TEXA-154, TEXA-160 | Completed | Verified (Demo-Ready) | 53/53 tests pass (100%) | Decoupled from 1300; optional collapsible GST section; claims conversion fixed with fullName
Customer Payments Received | TEXA-154, TEXA-162 | Completed | Verified (Demo-Ready) | 45/45 tests pass (100%) | Multi-invoice allocations; advance credit tracking; confirm/void double-entry journals
Vendor Payments Made | TEXA-154, TEXA-163 | Completed | Verified (Demo-Ready) | 26/26 tests pass (100%) | Disbursement lifecycle, bank balance deduction, and SCM supplier payment linkage
Treasury & Banking | TEXA-154, TEXA-160 | Completed | Verified (Demo-Ready) | 28/28 tests pass (100%) | Multi-bank accounts, IFSC validation, bank statement registration & GL reconciliation
Chart of Accounts (COA) | TEXA-154, TEXA-160 | Completed | Verified (Demo-Ready) | 25/25 tests pass (100%) | 5-type hierarchical account tree; balanced debit/credit ledger parent-child structure
General Ledger & Journals | TEXA-154, TEXA-160 | Completed | Verified (Demo-Ready) | 34/34 tests pass (100%) | Balanced double-entry journal vouchers, atomic GL balance sync & mirror reversals
GST Registry & Returns | TEXA-154, TEXA-167 | Completed | Verified (Demo-Ready) | 39/39 tests pass (100%) | GSTR-1, GSTR-3B, HSN reporting, GSTR-2B reconciliation & manual entry idempotency
Financial Reports | TEXA-154, TEXA-168 | Completed | Verified (Demo-Ready) | 17/17 tests pass (100%) | Balance Sheet (A=L+E), Profit & Loss, Trial Balance, Account General Ledger
Sales/Purchases Integration | TEXA-165, TEXA-167 | Completed | Verified (Demo-Ready) | 56/56 tests pass (100%) | Automated GL journal & GST postings from finalized invoices & purchase bills
Finance Settings | TEXA-154 | Completed | Verified (Demo-Ready) | 15/15 tests pass (100%) | Master list items for expense types, payment modes & configurable categories
Verified Automated Test Suite Results & Scope (As of 26 October 2026)
Test Suite Scope | Passed / Total | Pass Rate | Execution Date | Target Area / Invariant Covered | Command Executed
Operating Expenses & GST/ITC | 53 / 53 | 100% | 26-Oct-2026 | Ordinary expenses, blocked ITC absorption, claims conversion with fullName, account 1300 decoupling | pnpm --filter api test src/modules/finance/expenses
Full Finance Module Suite | 312 / 312 | 100% | 26-Oct-2026 | All 23 test files across Banking, COA, Expenses, GL, GST, Payments, Reports, Integration | pnpm --filter api test src/modules/finance
SCM Finance & Sales Suite | 62 / 62 | 100% | 26-Oct-2026 | Supplier bills, payments made, purchase orders, sales orders, accounts payable integration | pnpm --filter api test src/modules/scm
Financial Reports Suite | 17 / 17 | 100% | 26-Oct-2026 | Balance Sheet (A=L+E), P&L margins, Trial Balance debits=credits, GL running balance | pnpm --filter api test src/modules/finance/reports
Finance Integration Regression | 56 / 56 | 100% | 26-Oct-2026 | Cross-module sales-invoice & purchase-bill posting, GST idempotency, reversal symmetry | pnpm --filter api test src/modules/finance/integration ...
API Production Build (SWC) | 747 / 747 files | 100% | 26-Oct-2026 | Zero TypeScript compiler errors; SWC production bundle compiled cleanly | pnpm --filter api run build
UI TypeScript Typecheck | 0 errors | 100% | 26-Oct-2026 | Strict type-checking across all Next.js dashboard pages and Finance components | pnpm --filter ui run typecheck
Release Scope: Deferred Enhancements & Outstanding Live Verification
Item ID | Category | Feature / Item Description | Current State | Target Resolution / Justification | Classification
DEF-001 | Reporting | XLSX & PDF Export for Financial Statements | UI displays live interactive statement tables with print layout | Deferred to next sprint; print CSS serves browser export needs | Deferred Enhancement
DEF-002 | Reporting | Comparative Multi-Period Reporting (Prior Year / Quarter) | Single period and point-in-time snapshots supported | Deferred to Advanced Analytics release | Deferred Enhancement
DEF-003 | Treasury | Cash/Bank Treasury Summary Dedicated Tab | Backend endpoint /finance/reports/cash-bank-summary exists; UI uses Banking view | Planned for unified Treasury view consolidation | Deferred Enhancement
DEF-004 | Accounting | Automated Financial Period Closing Wizard | Period closing audit check API exists (/finance/reports/period-closing-status) | Workflow checklist ready for fiscal year-end sprint | Deferred Enhancement
VER-001 | Testing | Postman Live Verification on Disposable Test DB | Automated unit/repo tests 100% pass; 31 manual cases pass | Execute live suite against disposable PostgreSQL test container | Pending Verification
VER-002 | E2E Testing | Playwright Browser UI E2E Automated Suite | Components validated; harness safely aborted due to missing test DB container | Run Playwright specs once test DB container is provisioned | Pending Verification
BLK-001 | Integration | Direct SalesInvoice Database FK Constraints | Tracked via invoiceReference string in payments_received_allocations | Awaiting Sales module dedicated entity migration | Blocked / Dependency